## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today | 2025-09-12
Project Team Name | Visionaries
Project Topic | Credit Card Fraud Detection
Task |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[7 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[7 empty] | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20
| Data Cleaning & EDA | 2025-08-24 | 2025-08-27 | Abdulwahab | Cleaned dataset + EDA Report | Done | bar: 2021-11-01 to 2021-11-13
| Data Balancing | 2025-08-28 | 2025-08-29 | Shumukh & Wasmiah | Balanced datasets (Class Weight, ROS, SMOTE, RUS) | Done | bar: 2021-11-01 to 2021-11-12
| Logistic Regression - Train | 2025-08-30 | 2025-08-31 | Haneen | Trained Decision Tree model + evaluation results | Done | bar: 2021-11-01 to 2021-11-08
| Decision Tree - Train | 2025-09-01 | 2025-09-02 | Fatimah | Trained Random Forest model + evaluation results | Done | bar: 2021-11-01 to 2021-11-06
| Random Forest - Train | 2025-09-03 | 2025-09-04 | Abdulwahab | Trained Random Forest model | Done
| XGBoost - Train | 2025-09-05 | 2025-09-06 | Shumukh & Wasmiah | Trained XGBoost model | Done
| Logistic Regression - Evaluate | 2025-09-07 | 2025-09-08 | Haneen | Evaluation results for Logistic Regression (ROC-AUC, Precision, Recall, F1, Confusion Matrix) | Done
| Decision Tree - Evaluate | 2025-09-07 | 2025-09-08 | Fatimah | Evaluation results for Decision Tree (ROC-AUC, Precision, Recall, F1, Confusion Matrix) | Done
| Random Forest - Evaluate | 2025-09-07 | 2025-09-08 | Abdulwahab | Evaluation results for Random Forest (ROC-AUC, Precision, Recall, F1, Confusion Matrix) | Done
| XGBoost - Evaluate | 2025-09-07 | 2025-09-08 | Shumukh & Wasmiah | Evaluation Report + Metrics | Done
| LightGBM - Train | 2025-09-07 | 2025-09-08 | Bander | Trained LightGBM Mode | Done
| LightGBM - Evaluate | 2025-09-07 | 2025-09-08 | Bander | Evaluation Report + Metrics (ROC-AUC, Precision, Recall, F1) | Done
| Testing & Prediction - Run | 2025-09-09 | 2025-09-10 | Bander | Final Prediction Report + Results | Done
| Testing & Prediction - Final | 2025-09-09 | 2025-09-10 | Bander | Final predictions + summary report | Done
This date is illustration
These status are illustrations